## Sheet1
RazaKhanMohammad
PAP1
C201601
| Time Estimated | Actual Time | Difference
Phase 1 | (minutes) | (minutes) | (minutes)
A Course for Confidence | 45 | 30 | 15
WK 1: GoToTraining (GTT) | 60 | 75 | -15
Project Management Methodologies | 30 | 40 | -10
The Agile Development Methodology | 5 | 10 | -5
Waterfall Development Methodology | 7 | 12 | -5
Which Methodology Should I Pick: Agile vs Waterfall | 15 | 25 | -10
The Project Plan | 20 | 20 | 0
WK 1: Anchor Points | 30 | 45 | -15
WK 1: Call to Action - Success! | 60 | 140 | -80
WK 1: Research | 10 | 5 | 5
WK 1: Development | 60 | 140 | -80
Time Estimation & Management | 10 | 10 | 0
Assignment: Time Estimation & Management | 60 | 120 | -60
Wk 1: Project & Portfolio | 90 | 125 | -35
Total Time | 502 | 797
Cost | 22590 | 35865
Phase 2
The Burn-Up List | 60 | 60 | 0
WK 2: GoToTraining (GTT) | 60 | 65 | -5
What is a Portfolio? | 30 | 40 | -10
How Do I Create an ePortfolio? | 90 | 150 | -60
Self Evaluation: SWOT | 45 | 75 | -30
WK 2: Anchor Points | 20 | 25 | -5
WK 2: Call to Action - Failure to Success! | 90 | 70 | 20
Mission Statement | 60 | 60 | 0
WK 2: Research | 40 | 40 | 0
WK 2: Development | 60 | 90 | -30
Wk 2: Project & Portfolio | 60 | 100 | -40
Time Estimation & Management | 25 | 30 | -5
Total Time | 640 | 805
Cost | 28800 | 36225
Phase 3
The Burn-Up List | 60 | 25 | 35
WK 3: GoToTraining (GTT) | 60 | 55 | 5
Communicating with Clarity | 30 | 30 | 0
Communicating with Visual Tools | 90 | 120 | -30
WK 3: Anchor Points | 20 | 20 | 0
WK 3: Call to Action - Encouragement! | 90 | 130 | -40
WK 3: Research | 60 | 100 | -40
WK 3: Development | 120 | 170 | -50
Wk 3: Project & Portfolio | 60 | 120 | -60
Time Estimation & Management | 10 | 10 | 0
Total Time | 600 | 780
Cost | 27000 | 35100
Phase 4
The Burn-Up List | 60 | 15 | 45
WK 4: GoToTraining (GTT) | 60 | 50 | 10
WK 4: Anchor Points | 30 | 30 | 0
WK 4: Call to Action - Encouragement! | 90 | 60 | 30
WK 4: Research | 20 | 10 | 10
WK 4: Development | 60 | 70 | -10
WK 4: SWOT Follow-up | 30 | 40 | -10
WK 4: Being Paid for Your Work | 60 | 55 | 5
Wk 4: Project & Portfolio | 60 | 35 | 25
WK 4: Month in Review | 20 | 30 | -10
Time Estimation & Management | 10 | 10 | 0
Total Time | 500 | 405
Cost | 22500 | 18225
Total Month Cost | 100890 | 125415
Cost Difference | -24525
Rate | 45